## Sheet1 (hidden)
Decription | Nos | L | B | area | Remark
TERRACE
Terrace | 1 | 88.42 | 45 | 3978.9
| -1 | 32.33 | 23.17 | -749.0861
| -2 | 13.83 | 10.08 | -278.8128
| -1 | 9.42 | 5.42 | -51.0564
Vata | 2 | 88.42 | 1 | 176.84
| 2 | 45 | 1 | 90
| 4 | 13.83 | 1 | 55.32
| 2 | 23.17 | 1 | 46.34
|  |  | Total-A | 3268.4447
TANK
Tank | 1 | 30.83 | 22.67 | 698.9161
Vata | 2 | 30.83 | 1 | 61.66
| 2 | 22.67 | 1 | 45.34
|  |  | Total-B | 805.9161
CANOPY
canopy | 1 | 25 | 22 | 550
vata | 1 | 22 | 1 | 22 | sloping roof vata will be at one side only
| 1 | 19.25 | 13.83 | 266.2275
vata | 2 | 19.25 | 1 | 38.5
| 2 | 13.83 | 1 | 27.66
|  |  | Total-C | 904.3875
Total A+B+C |  |  |  | 4978.7483

## waterproofing- Brickbat
Ratio for waterproofing in 1:4 |  |  | Calculation
Summary of Brick bat plaster
Sr.no. | Description | 200 mm thk.
1 | Total Quantity of Brick-bat work in m3 | 1 | Qty in Sqm x depth of Brickbat
2 | 50% For mortar in cum (Dry Volume, Ratio-1:4) | 0.5 | Take 50% as a mortar
3 | Wastage 10% | 0.55 | Increase 10% as a wastage
4 | Wet Volume of Brick bat work Incresed for 35% | 0.7425 | Increse 35% for wet volume
5 | No. of cement bags | 4.2768 | {(Total wet volme of mortar*proprtion of Cement) / (sum of proportion)} * (density of cement/wt of 1 cement bag )
6 | Quantity of Sand in Cum | 0.594 | (Total wet volme of mortar*proprtion of sand) / (sum of proportion)
7 | Quantity of Sand in Cuft | 20.9682 | 1cumec= 35.3 Cuft
8 | Quantity of Sand in Brass | 0.20968 | 1brass=100cuft hence divde by 100
9 | Total No of Brick bats 4" | 325
10 | Total Bricks With 5% wastage | 341.25
11 | Area of Building | ----
12 | No of Bricks per Sft | ----

## waterproofing Basecoat
Material Calculation- Total Base coat |  |  | Claculation
Ratio for Waterproofing in 1:4
Summary of Base coat plaster
Sr.no. | Description | Quantity
1 | Total Quantity for plaster in Sqm | 10 | considered for 10 Sqm
2 | Dry Volume (Thickness is Average 2.54 cm i.e. 1") | 0.127 | area*thickness in m (average thickness is considered as 1")
3 | For wet volume quantity incresed by 35% | 0.17145 | Increase dry volume by 35% to get Wet volme
4 | Total no of cement bags | 0.98755 | {(Total wet volme of mortar*proprtion of Cement) / (sum of proportion)} * (density of cement/wt of 1 cement bag )
5 | Volume of sand in cum | 0.13716 | (Total wet volme of mortar*proprtion of sand) / (sum of proportion)
6 | Volume of sand in cuft | 4.8417 | 1cumec= 35.3 Cuft
7 | Volume of sand in Brass | 0.048417 | 1brass=100cuft hence divde by 100
8 | Additional 5% taken for Bulkage | 0.050838

## Labour work capacity
The capacity of doing work by an artisan or skilled labour in the form of quantity of work per day
Sr. No. | Description of work | Location | Quantity | Per day
1 | Brick work in lime or cement mortar | foundation and plinth | 1.25cum | (45cuft)per mason
2 | Brick work in lime or cement mortar | Superstructure | 1.00cum | (35cuft)per mason
3 | Brick work in mud mortar | foundation and plinth | 1.50cum | (55cuft)per mason
4 | Brick work in mud mortar | Superstructure | 1.25cum | (45cuft)per mason
5 | Brick work in lime or cement mortar | Arches | 0.55 cum | (20cuft)per mason
6 | Brick work in lime or cement mortar | Jack arches | 0.55 cum | (20cuft)per mason
7 | Half brick wall | Partition | 5.00sqm | (50sqft)per mason
8 | Coursed rubble stone masonry in lime cement mortar including dressing | - | 0.80cum | (30 cuft)per mason
9 | Coursed rubble stone masonry in lime cement mortar including dressing | - | 1.00cum | (35cuft)per mason
10 | Ashlars masonry in lime or cement mortar |  | 0.40cum | (15cuft)per mason
11 | Stone arch work | Arches | 0.40cum | (15cuft)per mason
12 | Lime Concrete | Foundation / Floor | 8.50cum | (300cuft)per mason
13 | Lime Concrete | Roof Terracing | 6.00cum | (200cuft)per mason
14 | Lime concrete 1:2;4 |  | 5.00cum | (175cuft)per mason
15 | RB work |  | 1.00cum | (35cuft)per mason
16 | RCC work |  | 3.00cum | (125cuft)per mason
17 | 12mm (1/2) plastering with cement or lime mortar |  | 8.00sqm | (80sqft)per mason
18 | Pointing with cement or lime mortar |  | 10.00sqm | (100sqft)per mason
19 | White washing or colour washing coats |  | 70.00sqm | (700sqft)per white washer
20 | White washing or colour washing coats |  | 200.00sqm | (2000sqft)per white washer
21 | Painting or varnishing doors or windows one coat |  | 25sqm | (250sqft)per painter
22 | Coal tarring or soligum painting one coat |  | 35.00sqm | (350sqft)per painter
23 | Painting large surface one coat |  | 35.00sqm | (350sqft)per painter
24 | Distempering one coat |  | 35.00sqm | (350sqft)per painter
25 | 2.5cm(1’) CC floor |  | 7.50sqm | (75sqft)per painter
26 | Flag store floor laying with lime or cement mortar excluding LC |  | 10.00sqm | (100sqft)per painter
27 | Brick on edge in floor lime or cement mortar excluding LC |  | 7.00sqm | (70sqft)per painter
28 | Brick bat floor as in above |  | 8.00sqm | (80sqft)per painter
29 | Timber framing sal or teak wood |  | 0.07cum | (2.5cuft)percarpenter
30 | Timber framing sal or country wood |  | 0.15cum | (5cuft)per carpenter
31 | Door and window shutters paneled or glazed |  | 0.15sqm | (7sqft) per carpenter
32 | Door and window shutters paneled or battened |  | 0.80sqm | (0.80sqft)percarpenter
33 | Sawing hard wood |  | 4.00sqm | (40sqft) per pair of sawers
34 | Sawing soft wood |  | 6.00sqm | (60sqft) per pair of sawers
35 | Single allahabad tiling or mangalore tiling |  | 6.00sqm | (60sqft) per tile layer
36 | Double allahabad tiling |  | 4.00sqm | (40sqft) per tile layer
37 | Breaking of brick ballest 40mm (11/2”) gauge |  | 0.75cum | (35cuft)per labourer or breaker
38 | Breaking of brick ballest 25mm (1”) gauge |  | 0.55cum | (20cuft)per labourer or breaker
39 | Breaking of stone ballest 40mm (11/2”) gauge |  | 0.40cum | (10cuft)per labourer or breaker
40 | Breaking of stone ballest 25mm (1”) gauge |  | 0.25cum | (10cuft)per labourer or breaker
41 | Ashlar stone dressing |  | 0.70cum | (25cuft)perstonecutter
42 | Flag stone dressing |  | 1.50sqm | (25sqft)perstonecutter
43 | Earthwork in excavation in ordinary soil |  | 3.00cum | (100cuft)per belder mazdoor
44 | Earthwork in excavation in hard soil |  | 2.00cum | (75cuft)per belder mazdoor
45 | Excavation in soil |  | 1.00cum | (35cuft)per belder mazdoor
46 | Number of bricks laid by a mason in brick work upto a height of 3m(10”) |  | 600 bricks per mason
47 | Amount of work done by a mazdoor helper per day
a. | Mix |  | 3.00cum | (100cuft)mortar per mazdoor
b. | Deliver brick |  | 4000 nos to a distance of 15m (50”) per mazdoor
c. | Deliver mortar |  | 5.5cum | (200cuft) per mazdoor
51 | Scaffolding cost for single storey building |  | Re.0.50per cum | (Rest.1.5%cuft) of brick work.

## labour req. as per qty
LABOUR (MAZDOOR) REQUIRED FOR DIFFERENT WORKS
Extracts from the report on productivity projects in building industries issued by National Building Organisation are given below:-
|  | Beldars | Mason | Mazdoor | Bhisti | Carpenter -II class | Backsmith / Fitter | Belder | Total
a) Earthwork per 28.30 cum (12000cuft)
1) Excavation in foundations, trenches etc., in ordinary soil including disposal up to 30m (100’) and lift of 1.5m(5ft) –5 beldars and 4 mazdoors can do 28.30 cum (1000cuft) per day. | 1000 Cuft | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 9
2) Refilling excavated earth in foundations, pointh etc, including consolidation in 15cm(6”) layers-3 beldars, 2 mazdoors and ½ bhisti can do 28.30 cum (1000cuft) per day. | 1000 Cuft | 3 | 0 | 2 | 0.5 | 0 | 0 | 0 | 5.5
3) Disposal of surplus earth within a lead of 30m (100’)-1 mazdoor can do 2.83cum (100 cuft) per day. | 100 Cuft | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
b) Cement concrete work per 2.83 cum (100cuft)
laying cement concrete – 2 beldars, 3 mazdoors, ¾ bhisti and ¼ mason, can do 2.83 cum (100 cuft) per day. | 100 Cuft | 2 | 0.25 | 3 | 0 | 0 | 0 | 0 | 5.25
c) R C C work:- | Qty | Beldars | Mason | Mazdoor | Bhisti | Carpenter -II class | Backsmith / Fitter | Belder | Total
1) Laying reinforced concrete – 3 beldars, 3 mazdoors, 1½ Bhisti and ½ mason can do 2.83 cum (100cuft) per day. | 100 Cuft | 3 | 0.5 | 3 | 1.5 | 0 | 0 | 0 | 8
2) Centering and shuttering for flat surfaces – 4 beldars and 4 carpenters (II class) can do 9.6sqm(96sqft) per day. | 100 Sqft | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 735
3)Reinforcement work for R C C –1 blacksmith or fitter and 1 beldar can bend and place in position 1 quintal (2 cwt) of steel per day. | 1 quintal | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 7911.54 | 395.577
[9 empty] | 0 | 39.5577 | 4.1206
d) Stone work per 2.83 cum (100cuft)- | [8 empty] | 0 |  | 16
[9 empty] | 0 |  | 16
Random rubble masonry with blue stone in foundations-3 masons, 3 beldars, 2 mazdoors and 1/4bhisti can do 2.83 cum (100cuft0 per day | 100 Cuft | 3 | 3 | 2 | 0.25 | 0 | 0 | 0 | 8.25
0
e) Brick work per 2.83 cum (100cuft)- | [8 empty] | 0
0
First class brick work in 1:4 cement mortar in superstructure partition walls, junctions of roof, parapet walls and string course – 2½masons,4½ mazdoors and 1/2 bhisti can do 2.83 cum (100cuft) per day. | 100 Cuft | 0 | 2.5 | 4.5 | 0.5 | 0 | 0 | 0 | 7.5 |  | 12.25
[9 empty] | 0 |  | 290.5
F) Wood work :- | [8 empty] | 0 |  | 101.675
0
1) For the frames of doors and windows –2 carpenters and 1 beldar can work 0.18 cum (6.40cuft) of wood equivalent to door frames 7.5cm x 10m of 1.2m x 2.1m (3’x4’of 3’x11’x7’)size per day. |  | 1 |  |  |  | 2 |  |  | 3
2) For paneled, glazed, etc, shutters-15 carpenters and 4 beldars can make and fix 4 shutters 40 mm thick of size 2.00m x 1.15m (1 ½ thick of size of 6’-9x 3’-9’) per day. Quantity of wood per shutter – 0.075 cum, ie2.66 cuft. |  | 4 |  |  |  | 15 |  |  | 19
g) Iron work :- | [8 empty] | 0
0
1) Fixing 40mm x 3mm=38cm(1 ½ “ x ½ ‘x 15”0 flat iron holdfasts-1 blacksmith (II class), I mason and I beldar can fix 36 holdfasts per day. | [8 empty] | 0
2) Fixing 16mm dia. 5/3” dia) M S rods –1 blacksmith (II class), 2 carpenters (II class) and 3 mazdoors can fix 16.5m (54rft) per day. | [8 empty] | 0
0
h) Flooring: - | [8 empty] | 0
4cm thick (1 1/2 “)thick cement concrete flooring of 40sqm (400sqft) require 5 masons, 4 beldars, 3 mazdoors and 1 bhisti per day for mixing laying and finishing. | 400 Sqft | 4 | 5 | 3 | 1 | 0 | 0 | 0 | 13
0
0
I) Finishing :- | [8 empty] | 0
0
1) Plastering with any mortar 12mm (5”) thick – 3 masons, 3 mazdoors and 1 bhisti can plaster 40sqm (400a ft) per day. |  | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 7
2)White washing or colour washing (3 coats) – 1 white washer and 1 mazdoor can do 60sqm (600sqft) per day. |  |  | 1 | 1 |  |  |  |  | 2
3) Painting two coats such as chocolate, red, grey, etc on wood are steel –3 | [8 empty] | 0
Painters and 2 mazdoors can paint 10sqm (100sqft) per day | [8 empty] | 0

## Material req. as per Std.
MATERIALS FOR DIFFERENT ITEMS OF WORKS
The requirement of materials for different items of works is as given below:-
Sl# | Particulars | Quantity
1. | Bricks (9” x 4 ½ “ x3” or 20 cm x 10cm x 10cm nominal size) for brick work | 1350 nos for 100cuft | 50000 nos per % cum (500nos.per cum)
2. | Dry mortar for brick work 30% | 30cuft for 100 cuft | 30cum for 100 cum
3. | Stone for rubble stone masonry 125% | 125cuft for 100 cuft | 125cum for 100 cum
4. | Dry mortar for rubble stone masonry 42% | 42cuft for 100 cuft | 42cum for 100 cum
5. | Bricks for brick ballast for lime concrete | 1050cuft for 100 cuft | 37000cum for 100 cum
6. | Brick bats or brick ballast for lime concrete | 150cuft for 100 cuft | 150cum for 100 cum
7. | Brick ballast for lime concrete | 100cuft for 100 cuft | 100cum for 100 cum
Sl# | Particulars | Quantity
8. | Dry mortar for lime concrete I foundation and floor 35% | 35cuft for 100cuft | 35cum for 100 cum
9. | Dry mortar for lime concrete in roof terracing 45% | 45cuft for 100cuft | 45cum for 100 cum
10. | Materials for cement concrete 1:2:4
| Ballast or grit 88% | 88cuft for 100cuft | 88cum for 100 cum
| Sand 44% | 44cuft for 100cuft | 44cum for 100 cum
| Cement 22% | 22cuft for 100cuft | 22cum (60 bags)for 100 cum
11. | Materials for 2.5cm (1”)cc 1:2:4 floor
| Stone grit | 8cuft for 100sqft | 2.40cum for 100 cum
| Sand | 4cuft for 100sqft | 1.20cum for 100 cum
| Cement | 2 ¼cuft (2 bags) for 100cuft | 0.08cum (24 bags)for 100 cum
12. | Bricks for R B work | 1200 nos for 100cuft | 42000nos/% cum(420 mps.[er ci,)
13. | Dry mortar for R B work 45% | 45cuft for 100cuft | 45cum for 100 cum
14. | Dry mortar for 12mm (1/2) plastering | 6cuft for 100sqft | 2.00cum for 100 sqm
15. | Dry mortar for pointing in brickwork | 2cuft for 100sqft | 0.60cum for 100 sqm
16. | Lime for white washing one coat | 1kg for 100sqft | 10kg for 100 sqm
17. | Dry distemper for ist coat | 0.65 kg for 100sqft | 6 ½ kg for 100 sqm
18. | Dry distemper for 2nd coat | 0.50 kg for 100sqft | 5kg for 100 sqm
19. | Snow-Cem for Ist coat | 3kg for 100sqft | 30kg for 100 sqm
20. | Snow-Cem for 2nd coat | 2kg for 100sqft | 20kg for 100 sqm
21. | Paint ready mixed for painting one coat | 1/3gl.for 100sqft | 10ltr for 100 sqm
22. | Paint (stiff) for painting one coat | 1kg for 100sqft | 10kg for 100 sqm
23. | Bricks (20 x 10 x 10cm) for brick floor or half brick wall | 500 nos for 100sqft | 5000nos.for 100sqm
24. | Dry mortar for brick floor or half brick wall | 12cuft for 100sqft | 3.20 cum for 100 sqm
25. | Bricks (9” x 4 ½ “ x3”) for brick flat work | 350 nos for 100sqft | 3500nos.for 100sqm
26. | Dry mortar for brick flat floor | 8cuft for 100sqft | 2.25cum for 100 cum
27. | Bricks (9” x 4 ½ “ x3”) required for honey comb wall | 325 nos for 100sqft | 3250 nos.for 100sqm
28. | Dry mortar for honey comb wall | 8cuft for 100sqft | 2.5cum for 100 cum
29. | Materials for 2cm (3/4”)thick damp proof course of 1:2 cement mortar
| Cement | 3cuft (2.5bags) for 100sqft | 0.90cum (27 bags)for 100 cum
| Sand | 6cuft for 100sqft | 1.80cum for 100 cum
| Compound or impermo @ 1kg per bag of cement | 2.5kg for 100sqft | 27kg for 100 sqm
30. | Materials for 2.5cm (1”)cc 1:1 ½ :3 damp proof course
| Stone grit | 8cuft for 100sqft | 2.25cum for 100 cum
| Sand coarse | 4cuft for 100sqft | 1.13cum for 100 cum
| Cement | 2 ½ cuft (2 ½ bags) for 100sqft | 0.75cum for (221/2bags)for100 cum
| Compound or impermo @ 1kg per bag of cement | 21/2 kg for 100sqft | 22½ kg for 100 sqm
31. | Bitumen or asphalt for painting on D P C or on roof – 1st coat | 15 kg for 100sqft | 150 kg for 100 sqm
| 2nd coat | 10 kg for 100sqft | 100 kg for 100 sqm
32. | G G I sheet for roof | 128sqft for 100sqft | 128 sqmfor 100sqm
33. | A G corrugated sheet for roof | 115sqft for 100sqft | 115 sqmfor 100sqm
34. | Timber for paneled door shutter 4cm (1 ½”) thick | 15cuft for 100sqft | 4.5 cum for 100 cum
35. | Timber for battend door shutter 4cm (1 ½”) thick | 13cuft for 100sqft | 4.0 cum for 100 cum
36. | Timber for paneled & glazed shutter 4cm (1 ½”) thick | 11cuft for 100sqft | 3.0 cum for 100 cum
| Timber for fully glazed shutter 4cm (1 ½”) thick | 8cuft for 100sqft | 2.0 cum for 100 cum

## Sheet3
Daily Progress Report
Daily Report No. |  |  | Date:
Project Name: |  |  | Day:
Location | Description of work | Status of work | Responsible Engineer
35.2876

## Attendence Sheet
January |  |  |  |  | February |  |  |  |  | March
Date | Day | In | Out | Remark | Date | Day | In | Out | Remark | Date | Day | In | Out | Remark
2015-01-01 | Thu | 0:00 | 0:00 | Holiday | 2015-02-01 | Sun |  |  |  | 2015-03-01 | Sun
2015-01-02 | Fri | 10:52 | 7:10 | 18 min Extra | 2015-02-02 | Mon |  |  |  | 2015-03-02 | Mon
2015-01-03 | Sat | 10:34 | 6:40 | 5 min Extra | 2015-02-03 | Tue |  |  |  | 2015-03-03 | Tue
2015-01-04 | Sun | 0:00 | 0:00 | Holiday | 2015-02-04 | Wed |  |  |  | 2015-03-04 | Wed
2015-01-05 | Mon | 10:55 | 7:05 | 10 min Extra | 2015-02-05 | Thu |  |  |  | 2015-03-05 | Thu
2015-01-06 | Tue | 10.58 | 7.3 | 32 min Extra | 2015-02-06 | Fri |  |  |  | 2015-03-06 | Fri
2015-01-07 | Wed | 10:52 | 6:54 | 2 min Extra | 2015-02-07 | Sat |  |  |  | 2015-03-07 | Sat
2015-01-08 | Thu | 10:51 | 7:39 | 45 min Extra | 2015-02-08 | Sun |  |  |  | 2015-03-08 | Sun
2015-01-09 | Fri | 11:00 | 7:00 | - | 2015-02-09 | Mon |  |  |  | 2015-03-09 | Mon
2015-01-10 | Sat | 10:50 | 7:15 | 25 min Extra | 2015-02-10 | Tue |  |  |  | 2015-03-10 | Tue
2015-01-11 | Sun | 0:00 | 0:00 | Holiday | 2015-02-11 | Wed |  |  |  | 2015-03-11 | Wed
2015-01-12 | Mon | 11:18 | 7:10 | Late | 2015-02-12 | Thu |  |  |  | 2015-03-12 | Thu
2015-01-13 | Tue | 11:01 | 4.:00 | Took Half day | 2015-02-13 | Fri |  |  |  | 2015-03-13 | Fri
2015-01-14 | Wed | 11:06 | 7:25 | 20 min Extra | 2015-02-14 | Sat |  |  |  | 2015-03-14 | Sat
2015-01-15 | Thu | 10:52 | 7:27 | 35 min Extra | 2015-02-15 | Sun |  |  |  | 2015-03-15 | Sun
2015-01-16 | Fri | 10:48 | 7:15 | 20 min Extra | 2015-02-16 | Mon |  |  |  | 2015-03-16 | Mon
2015-01-17 | Sat | 10:53 | 6:45 | 10 min Early | 2015-02-17 | Tue |  |  |  | 2015-03-17 | Tue
2015-01-18 | Sun | 0:00 | 0:00 | Holiday | 2015-02-18 | Wed |  |  |  | 2015-03-18 | Wed
2015-01-19 | Mon | 10:59 | 7:17 | 17 min Extra | 2015-02-19 | Thu |  |  |  | 2015-03-19 | Thu
2015-01-20 | Tue | 10:55 | 7:15 | 20 min Extra | 2015-02-20 | Fri |  |  |  | 2015-03-20 | Fri
2015-01-21 | Wed | 10:50 | 7:25 | 30 min Extra | 2015-02-21 | Sat |  |  |  | 2015-03-21 | Sat
2015-01-22 | Thu | 11:02 | 7:12 | 10 min Extra | 2015-02-22 | Sun |  |  |  | 2015-03-22 | Sun
2015-01-23 | Fri | 10:54 | 7:01 | 5min Extra | 2015-02-23 | Mon |  |  |  | 2015-03-23 | Mon
2015-01-24 | Sat | 11:04 | 7:10 | 5 min Extra | 2015-02-24 | Tue |  |  |  | 2015-03-24 | Tue
2015-01-25 | Sun | 0:00 | 0:00 | Holiday | 2015-02-25 | Wed |  |  |  | 2015-03-25 | Wed
2015-01-26 | Mon | 0:00 | 0:00 | Republic Day | 2015-02-26 | Thu |  |  |  | 2015-03-26 | Thu
2015-01-27 | Tue | 10:58 | 7:00 | - | 2015-02-27 | Fri |  |  |  | 2015-03-27 | Fri
2015-01-28 | Wed | 10:56 | 7:00 | went Shri vardhan | 2015-02-28 | Sat |  |  |  | 2015-03-28 | Sat
2015-01-29 | Thu | 11:07 | [7 empty] | 2015-03-29 | Sun
2015-01-30 | Fri | [8 empty] | 2015-03-30 | Mon
2015-01-31 | Sat | [8 empty] | 2015-03-31 | Tue
Note on E8: Ashish: Went at Mandwa site
Note on E11: ashish: Went at Nahur Site. @ 11am
Note on E23: Administrator: Went to Kamraj nagar Site as per Karan sir Instruction.

## Sheet1 (2)
Work Schedule |  |  | 3rd Dec 2014
Sr. No. | Project | Work | Completion Date
1 | Kamraj Bagar Sale Building | BBS | Completed & File prepared
2 | Kamraj Nagar Rehab Bldg No-1 | BBS | Completed & File prepared
3 | Kamraj Nagar Rehab Bldg No-2B | BBS | Completed & File prepared
4 | Spiro Tower sale Bldg -Mulund | BBS | Completed & File prepared
5 | Spiro Tenant Bldg -Mulund | BBS | Completed & File prepared
6 | Spiro Tower Aproximate costing | Approx Costing | Done
7 | Nahur Tower -2 | BBS | Already Started Will Be completed till 15th Dec 14
8 | Nahur Tower -2 | Complete Abstract | Till 15 jan 2015
9 | Nahur Tower-1 | BBS
10 | Nahur Tower-1 | Complete Abstract
9
10
Note: For Abstract preaparation complete Specification of materials will be required.

## Bldg Details
Neelam Realtors all Site Details
Site/project name | Building Name | Storied | Wings | Type Of Flats | No. Of Flats/Floor in Each Wing | Total Refuge Flats | Total Flats | Total B.U.A Area in Sq.Ft | Extra Amenities | Civil Contractor
Star Premises | Spiro Sale | Gr.+ 5pod +17 Resi. | - | 2 & 3Bhk | 1 Flat | 3-2bhk | 14-3Bhk, 3-2BHk | 44335 | Health club, Society office at 5th Pod Floor & 4shops @ G.F.
| Spiro Tenant Bldg | Gr.+7 floors | - | 1-Bhk | 5 flats | - | 35+2 @GF (1Bhk) | 15767 | Balwadi, Soc. Off, welfare centre @ G.F.
Kamraj Nagar | Solscite Sale Bldg | Base+ 3 pod +25 Resi. | Setaria | 3-2BHk, 2-2.5Bhk & 1-3Bhk | 6 Flats | -
|  | Base+ 3 pod +25 Resi. | Saveria | 3-2BHk, 2-2.5Bhk & 1-3Bhk | 6 Flats | -
Rehab. Bldg-1
Rehab Bldg-2A
Rehab Bldg-2B
Senroof | Tower-1 | Stilt+2 Pod. +28 Resid. | Serena
Sanctura
| Tower-2 |  | Silvino
Sanino
Tower-3
Tower-4